## Sheet 1
PS20210663 - Consultant for Park Design and Construction Administration for a New Park at East Fraser Lands
APPENDIX 3 - COMMERCIAL PROPOSAL
Tasks | Discipline | Title | Name | Hourly Rate | Total Hours | Total Price
Project Start Up
Project Kickoff Meeting |  |  |  | 0 |  | 0
Initial Meeting and Exploration and Review of Park Documents |  |  |  | 0 |  | 0
Project Start Up Total |  |  |  |  | 0 | 0
Phase 1 – Design Package and Report
Part 1 – Design Development and Working Drawings
Design Refinement |  |  |  | 0 |  | 0
Preparation of Drawings, Specifications and Technical Design |  |  |  | 0 |  | 0
Design Review with Park Operations Staff at the 50%, 75%, and 95% design intervals |  |  |  | 0 |  | 0
Design Approval, Permit and Coordination |  |  |  | 0 |  | 0
Any other tasks as per scope of work to complete the project |  |  |  | 0 |  | 0
Part 1 - Design Development and Working Drawings Total |  |  |  |  | 0 | 0
Par
Part 2 - Tender Phase
Assist with ITT documents, including clariciations from bidders and bidder selection |  |  |  | 0 |  | 0
Attend Bidders Meeting (1) |  |  |  | 0 |  | 0
Any other tasks as per scope of work to complete the project |  |  |  | 0 |  | 0
Part 2 - Tender Phase Total |  |  |  |  | 0 | 0
Part 3 - Construction Administration
Issued for Construction contract documents |  |  |  | 0 |  | 0
Monitoring construction and attending at least one on-site meeting every two weeks during the duration of construction,review contract changes that effect the design, and provide meeting minutes. |  |  |  | 0 |  | 0
Preparing site instructions, contemplated change orders, change directives and site clarifications. Review project submittal as shop drawings, product data, and samples |  |  |  | 0 |  | 0
Review progress draw and issue payment certificate and leading the substantial completion process |  |  |  | 0 |  | 0
Issuing final acceptance in collaboration with Park Board |  |  |  | 0 |  | 0
One year warranty review |  |  |  | 0 |  | 0
Provision of final as-built drawings |  |  |  | 0 |  | 0
Any other tasks as per scope of work to complete the project |  |  |  | 0 |  | 0
Part 3 - Construction Administration Total |  |  |  |  | 0 | 0
Other item(s) as necessary |  |  |  | 0 |  | 0
Total Hours | [5 empty] | 0
Total Disbursements | [5 empty] | 0
Total Price before tax | [5 empty] | 0