## PS20190780
[Organisation Name and contact details]
THE CITY OF VANCOUVER |  | PRJT MGMT | ENGINEERING |  |  | ELECTRICAL | STRUCTURAL | ARCHAEOLOGAL | FIELD SERVICES |  | OTHER | OTHER | ESTIMATED | ESTIMATED | TOTAL
Burrard Pump Station Refurbishment |  | Name | Name | Name | Name | Name | Name | Name | Surveyor | Inspector | Name | Name | FEES | DISBURS. | FEES
Estimated Fees and Disbursements Insert Hourly Rate ---> | [12 empty] | $ | $ | $
1 | Conceptual Design Servces
1.1 | Project Startup Meeting | [11 empty] | 0 |  | 0
1.2 | Background Information Review & Site Visit | [11 empty] | 0 |  | 0
1.3 | Archaeological Overview Assessment Study | [11 empty] | 0 |  | 0
1.4 | Hydraulic Transient Analysis | [11 empty] | 0 |  | 0
1.5 | Conceptual Design (Sketches, Cost Benefit Analysis, Review Meeting) | [11 empty] | 0 |  | 0
1.6 | Other (Please Specify) | [11 empty] | 0 |  | 0
| Sub-total Conceptual Design Servces | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Detailed Design & Specifications
2.1 | 50% Design (Drawings, Specifications, Design Report, Cost Estimate, Review Meeting) | [11 empty] | 0 |  | 0
2.2 | 90% Design (Drawings, Specifications, Design Report, Cost Estimate, Review Meeting) | [11 empty] | 0 |  | 0
2.3 | 100% Design (Drawings, Specifications, Design Report, Cost Estimate, Review Meeting) | [11 empty] | 0 |  | 0
2.4 | Other (Please Specify) | [11 empty] | 0 |  | 0
| Sub-total Detailed Design & Specifications | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Construction Tendering Services
3.1 | Tender and Contract Documents | [11 empty] | 0 |  | 0
3.2 | Attend Tender Bid Meeting | [11 empty] | 0 |  | 0
3.3 | Prepare Responses to Technical Questions | [11 empty] | 0 |  | 0
3.4 | Evaluate and Recommend Tender Award | [11 empty] | 0 |  | 0
3.5 | Quality Management Plan | [11 empty] | 0 |  | 0
3.6 | Other (Please Specify) | [11 empty] | 0 |  | 0
| Sub-total Construction Tendering Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Construction & Contract Administration Services
4.1 | Prepare "Issued for Construction" Drawings and Specifications | [11 empty] | 0 |  | 0
4.2 | Construction Start-Up Meeting | [11 empty] | 0 |  | 0
4.3 | Shop Drawings | [11 empty] | 0 |  | 0
4.4 | Contract Administration Services | [11 empty] | 0 |  | 0
4.5 | Inspections, Field Reviews, & Site Meetings | [11 empty] | 0 |  | 0
4.6 | Start Up & Commissioning | [11 empty] | 0 |  | 0
4.7 | Other (Please Specify) | [11 empty] | 0 |  | 0
| Sub-total Construction & Contract Administration Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Project Wrap-Up Documentation
5.1 | Commissioning Report | [11 empty] | 0 |  | 0
5.2 | Project Wrap-Up Report | [11 empty] | 0 |  | 0
5.3 | Prepare and Seal Record Drawings & Letters of Assurance | [11 empty] | 0 |  | 0
5.4 | Lessons Learned Review Meeting | [11 empty] | 0 |  | 0
5.5 | Other (Please Specify) | [11 empty] | 0 |  | 0
| Sub-total Project Wrap-Up Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Miscellaneous Items
6.1 | Electrical Permit Application | [11 empty] | 0 |  | 0
6.2 | BC Hydro Coordination | [11 empty] | 0 |  | 0
6.3 | Project Management Tasks | [11 empty] | 0 |  | 0
6.4 | End of Warranty Inspection & Report | [11 empty] | 0 |  | 0
6.5 | Other (Please Specify) | [11 empty] | 0 |  | 0
| Sub-total Miscellaneous Items | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Project Fees (exclusive of GST) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Provisional Items
7.01 | PLC Programming | [11 empty] | 0 |  | 0
7.02 | Additional Meetings (price per single meeting) | [11 empty] | 0 |  | 0
7.03 | Additional costs required for Back-Up On-Site Generator | [11 empty] | 0 |  | 0
7.04 | Additional costs required for Asbestos Removal Plan | [11 empty] | 0 |  | 0
7.05 | Additional costs required for Electrical Room Expansion above 2050 FCL | [11 empty] | 0 |  | 0
7.06 | Other (Please Specify) | [11 empty] | 0 |  | 0
7.07 | Other (Please Specify) | [11 empty] | 0 |  | 0
7.08 | Other (Please Specify) | [11 empty] | 0 |  | 0
7.09 | Other (Please Specify) | [11 empty] | 0 |  | 0
7.1 | Other (Please Specify) | [11 empty] | 0 |  | 0
| Total Provisional Items (exclusive of GST) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PLEASE NOTE:
The proponent may include additional payment line items at their discretion.
For proposed support staff, provide hourly rates including all costs for salary, benefits, profit
and any other employment related expenses.
For personnel proposed that currently resides outside of the Metropolitan Vancouver area
provides the expected per diem for all meals, accommodation and travel costs.
All prices are to be exclusive of applicable sales taxes calculated upon such prices, but
inclusive of all other costs.